## Slide 1: Project: REDIRECT
Reducing, Emergency detentions by intervening, responding, engaging calmly and together

## Slide 2: Project: REDIRECT
Pete Zallar- Change Leader/Crisis Stabilization Team Leader
Brad Schlough- Executive Sponsor/Director of Community Services
Hannah Flanagan- Change Team Member/Manager of Emergency Serivces
Amalia Becker- Inpatient Discharge Planner/Change Team Member

## Slide 3: PROJECT AIM
Decrease number of involuntary hospitalizations
  FROM BASELINE 29.5 PER MONTH
  TO 26.5 PER MONTH

## Slide 4: Objective of 1st Rapid Cycle
Decrease number of non-emergent tasks done by crisis workers and emergency telephone workers-delegate to non-emergency staff
Provide a more person-centered less authoritative approach to crisis support, by bringing in paraprofessionals and peer support staff to on-sight crisis intervention

## Slide 5: Change
Add Outreach Workers (ORWs) 5p-10p for after hours crisis unit support.
Replace a crisis worker with an ORW as the second staff on evening home-visits.
ORW to provide medication observation in lieu of ETS worker completing that task

## Slide 6: Results
Decreased non-emergent tasks being completed by crisis workers and ETS staff thus reducing their overall feeling of stress during their shift
Increased number of mobile responses completed by crisis workers on the evening shift.
**After Oct 31 will be able to provide number of EDs/Hospitalizations that were reduced through change project

## Slide 7: Next Steps
Increasing the number of non-emergent tasks ORWs can assist with in the evening to include: checking out medications for delivery, making reminder calls to clients for next day appointments
Additional education for Crisis Workers to reduce their anxiety over having ORWs and/or Peer Support staff join them on appointments- thus increasing their willingness to follow through and have ORWs join appointments

## Slide 8: Impact
During the first 2-week cycle, ORWs were able to join crisis workers on 4 occasions. Their availability to join home-visits freed the other Crisis Staff who were then able to tend to other emergent tasks.
By adding ORWs to do medication observations, it has reduced the ETS workers anxiety over having to put high risk callers on hold to observe medications as they have had to do in the recent past. This also increased the quality of care ETS can provide to callers in crisis.