## Slide 1: Accessing Services Juneau County Department of Human Services
JoAnn Geiger, LPC Behavioral health and clinic manager—change leader
Mary Jo Onsager, LCSW community support program manager—change leader
Scott ethun director—executive sponsor
Ruthie gregar, rn behavioral health and clinic nurse—team member
Mandy schmidt Intake worker—team member
Penny janechek Office manager—team member
Pat morris intake worker—team member
Deb crawford billing specialist—team member

## Slide 2: Project Aim
Big Aim
  Reduce the amount of emergency detentions by getting consumers the right services in a more timely fashion
Small Aim
  Reduce the amount of time it takes for new consumers to see a therapist from the time they call in for services
    Baseline data reported that it was taking 13.6 days from call in to face to face session with therapist
    Goal: Reduce the amount of time it takes between first contact to the time a new consumer sees a therapist from 13.6 days to 10 days.

## Slide 3: Changes
Original Intake Process
Changed Intake Process
1/1/15 assignments occurred once a week
There was no separate billing/financial appointment
1/1/15 full time therapists (2) were to have 3 intake slots a week to accommodate new intakes.
On 4/1/15 we began assigning cases on a daily basis versus once a week--ADOPTED
On 4/1/15 at the time of the initial call, the consumer was transferred to billing to schedule a separate appointment--ABANDONED
On 4/1/15 we also instituted that our nurse would meet on the same day as the billing appointment to get releases signed and collect information and schedule the intake with the therapist.--ADAPTED
Notes: Original process
From 1/1/15 through 3/30/15 our intake process did not include a separate billing/financial appointment
Consumer assignments were done every Wednesday at staffing
Changed process
From 4/1/15 through 7/31/15 consumers had to schedule a separate appointment to come in a meet with billing prior to being scheduled to see a therapist
Consumer assignments were done on any day of the week
We have now abandoned this change process as our results did not reduce the time.

## Slide 4: Results
Initial Data Points
Change Data Points
Data from 1/1/15 through 3/4/15
Average time from call in to being assigned to a therapist was 3.3 days
Average time from call in to face to face intake with a therapist was 13.6 days
Data from 4/1/15 through 7/31/15
Average time from call in to being assigned to a therapist was .9 days
Average time from call in to face to face intake with a therapist was 26.9 days
Notes: 1/1/15-3/4/15 we looked at 20 new mental health consumers
4/1/15-7/31/15 we had 35 new mental health consumers
Due to the findings we:
Adopted the assigning cases daily
Adapted the Nurse portion: now new consumers will see an I&R worker (therapist) who will screen, get ROI’s etc.
Abandoned the financial appointment prior to seeing a therapist.
We had historical data telling us that having a separate billing appointment helped decrease our no show rate, which is why we went to the change process we went to. However, we had to weigh the advantages/disadvantages when looking at our overall goal of getting new consumers to a face to face with a therapist faster.

## Slide 5: Next Steps
Taking what we have learned from our rapid cycle, we sat down with both support staff and clinic staff to get input and feedback on how we make this process better
Starting 9/28/15
  New Consumers are assigned on a daily basis
  Consumers are giving an Information and Referral appointment within 48 hours of call in with a therapist/substance abuse counselor
  After Information and Referral, if consumer will be enrolled in services at JCDHS the worker will walk consumer over to billing to gather that information after the appointment
Notes: New intake process includes new clients for MH services will be seen within 48 hours for an information and referral appointment. At that appointment the therapist/worker will gather pertinent information regarding clients/consumers needs and then either set them up for a full mental health intake or refer them to other community resources, programs, etc. If the consumer will stay at JCDHS for programs the I&R worker will take them over to billing after their initial I&R appointment to gather financial information.

## Slide 6: Impacts
Change team and other staff strongly agree that we need to be consumer focused and strength based
Increased multiple teams/units working together to make the process better
Continue to look at how we get consumers to the right programs/services
Continued momentum forward for change
Notes: One of our biggest challenges was getting to a shared perspective. Change can be scary for those who have not had any changes in the past 11 years. However, once the team members felt that they had a voice and could see the results of change (good or bad) they were able to have ownership in the change process and were more apt to move forward with change.