## Slide 1: La Crosse County Comprehensive Community Services
2015 NIATx Project
Change Team
Gail Elland – Change Leader
Emily McGonigle
Ingrid Herken
Ashley Merchlewitz
Pam Bendel
Greg Nekoli
Paul Brown
Team Sponsor
Christin Skolnik

## Slide 2: AIM
Decrease the amount of non-billable MA time for CCS due to late paperwork
Chart: 2015 Non Billable MA Days
Chart: 2015 Unbillable MA Days
| 2015 | January | February | March | April | May | June | July | August | September | October | November | December
 | 156 | 167 | 51 | 39 | 6 | 8 | 0 | 3

## Slide 3: Change
  Created QA reminder sheet
  Created a staff checklist that is attached to each intake packet.
  Met with staff to discuss staff tracking of paperwork
  Tightened up supervisor notification of late plans
  Streamlined records request from collaborating partners
  Staff directly hands paperwork to identified QA staff

## Slide 4: RESULTS
Decrease the number of non-billable CCS days due to paperwork not completed on time.
Non-billable days decreased from 482 to 430, which was a 10.8% decrease
Clients enrolled in system went from 140 to 276, which was a 49.3% increase
Chart: 2014 Non-billable MA Days
Chart: 2014 Non-billable MA Days
Chart: 2014 vs 2015 Caseload
 | 140 | 276

## Slide 5: Impact
County
  CRS Funding
  Crisis Funding
  CCS Funding
  Reduced stress for staff
Consumer/Vendor
  Positive financial impact
  expenses related to CCS and Crisis funding
  Provided constant interventions for clients

## Slide 6: Next Steps
Continue to monitor QA
Expand to all WRIC counties
Work on refining internal processes
  Decreasing non-billable days related to internal processes
  New computer software will streamline work/billing process as of 10/01/2015 ????