## Slide 1: Reducing Hospitalization Frequency Price Co. Health and Human Services
Team Members:
Kathy Billek, Executive Sponsor and Change Leader; Kelly Schultz and Dave Dettmering, Donald Yahn, Rhonda Lleweyn, Rebecca Dennis, Crisis on call staff; Tracie Burkart

## Slide 2: THE AIM Reduce %age of crisis calls resulting in hospital admission by 10%, from 27% to 24%, by Dec. 31, 2015
The problem
In the first 6 months of 2015 hospitalization rates increased but chapters dropped due to no probable cause
  75 evaluations, 20 people admitted in the first 6 months of 2015
  Over 75% are dismissed

## Slide 3: CHANGES
Identified process problem: Staff are uncomfortable with decision making using current tools and available resources.
Change: Embed the Columbia Suicide Severity Rating Scale in the existing emergency assessment.
PLAN: Train on-call staff on new assessment (CSSRS)
DO: on-call staff to watch and review on-line information
STUDY: on-call staff did not follow through
ACT: Adapt.
1:1 meeting and group training with on-call staff on new assessment

## Slide 4: IMPACT
Staff Perspective: More time available to do collaborative planning with client rather “kneejerk” reactions to crisis.
Consumer Perspective: decreased trauma related to hospitalization; Importance of maintaining community connections (job, family, etc.)
Business perspective: 10% reduction in hospital admissions in the next 6 months = 2 fewer admissions = potential cost savings of $3,000.00

## Slide 5: Lessons Learned
Collaboration attempted with contractual provider with verbal agreement on ideas but no follow through.
Administrative buy-in is important; need to engage management of the contracted provider
Long term contractual provider limited alternative to no alternative options.

## Slide 6: NEXT STEPS
Work on a MOU/Contractual agreement that spells out the expectations and next steps for the provider:
    Becoming more active on change teams
    Complete NIATx limited training to understand change process
Plan for training for all crisis on call staff for new form; review expectations of using form and identify start date.