## Slide 1: TRIAGE RESTRUCTURE
Washington County Human Services Department

## Slide 2: Triage Restructure - Aim
1 – Reduce Re-hospitalizations
January – September 2015 data
39 re-hospitalizations within 30 days
5 clients had 3 admissions
2 clients had 4 admissions
And additional 11 clients had 2 hospitalizations in that timeframe, but more than 30 days passed between those admissions.

## Slide 3: Changes Made
Prior to October 2015
  Triage met every Tuesday & Thursday for 1 hour.
  Participants included Chapter 51 Liasion, 3 program supervisors, 1 clinical supervisor
  Issues – direct staff were not present. Admissions and discharges occurred between meeting dates and proper planning could not be done.
Starting October 2015
  Triage meets daily for 1 hour
  Agenda is created to discuss most time sensitive or critical cases
  All direct staff are available & required to attend if their client is on the agenda

## Slide 4: Results
So far –
  The agenda is helping keep the meeting focused
  Staff are feeling more involved in their clients hospitalization and discharge plans
  Chapter 51 liaison is able to provide more helpful information about clients to the hospital staff
  No data on re-hospitalizations yet.

## Slide 5: Next Steps
Continue to collect data regarding re-hospitalization rates
Structure the agenda further. Currently only identifies names of clients. Will expand to include what the discussion about that client needs to include. For example: is the home safe, is the alcohol disposed of, what is the baseline, what meds have been tried in the past?

## Slide 6: Impact
Lessons Learned
  Good communication is key
  Choose words wisely – needing to make a change does not mean staff have done wrong
  Remember this is a test that can be modified