## Slide 1
Diversion Conversion
Presented by:
Kelly Randall, RN
Becky Manning, RN, APNP
Grant/Iowa Counties

## Slide 2: AIM ADDRESSED
INCREASE HOSPITAL DIVERSIONS DECREASE EMERGENCY DETENTIONS
  *From May 1st-September 30th 2010
  -316 Crisis Contacts
  -42 Emergency Detentions (14%)
  -59 Diversions (19%)
  *From May 1st-September 30th 2011
  -390 Crisis Contacts
  -50 Emergency Detentions (13%)
  -41 Diversions (11%)

## Slide 3: CHANGES
#1 CRISIS DIVERSION BED “SAFE PLACE”
  Provide a crisis diversion bed as an alternative to an ED
  #2 DEVELOP CRITERIA FOR URGENT APPOINMENTS
  Prioritize urgent appointments
  #3 STAFF TRAINING
  In-service for agency staff
  #4 URGENT APPOINTMENT SLOTS
  Daily scheduled urgent appointments in each clinic
  #5 URGENT APPOINTMENT SLOTS
  Daily scheduled urgent appointments in one clinic
  #6 URGENT APPOINTMENT SLOTS
  Daily scheduled urgent appointments in each clinic

## Slide 4: DATA
Plan Change #1
3 “Safe Place” Admissions over a 6-month period
2 Emergency Detentions
Plan Change #2
1 Hour Urgent Appointments scheduled at each clinic
Tracking System Developed
Urgent Appointment Triaged according to Highest Priority
Plan Change #3
All staff educated on Urgent Appointment Procedure
Plan Change #4
May-August Lancaster 8/72
May-August Dodgeville 11/80
Plan Change #5
September Lancaster 5/13
September Dodgeville 2/6
Plan Change #6
Implemented October 1st, 2011

## Slide 5: BOTTOM LINE DATA
41 Hospitalizations Diverted from 5/1 through 9/30.
Average Hospital Stay Costs the county $3000
SAVINGS=$123,000

## Slide 6: ADOPTED, ADAPTED, ABANDONED
#1 CRISIS DIVERSION BED “SAFE PLACE”
Abandoned: Not Utilized
  #2 DEVELOP CRITERIA FOR URGENT APPOINMENTS
  Adopted
  #3 STAFF TRAINING
  Adopted
  #4 URGENT APPOINTMENT SLOTS
  Adapted: Number of Daily Urgent Appointment Slots Decreased by 50%
  #5 URGENT APPOINTMENT SLOTS
  Adapted: Number of Daily Urgent Appointment Slots Increased by 50%
  #6 URGENT APPOINTMENT SLOTS
  Adopted

## Slide 7: Future Plans
CONTINUE TO UTILIZE CHANGES IMPLEMENTED WITH FIRST NIATX CHANGE PROJECT
CONTINUE TO UTILIZE CHANGES IMPLEMENTED WITH SECOND NIATX CHANGE PROJECT
CONTINUE TO UTILIZE THE NIATX CHANGE MODEL TO IMPLEMENT FUTURE CHANGES TO IMPROVE OUR AGENCY AND THE WAY WE SERVE OUR CLIENTS