## Slide 1
Hospital Follow-Up Care: Reducing No-Shows – NIATx Project 2013

## Slide 2
North Central Health Care | NIATx Project 2013
Big AIM
Decrease Inpatient Behavioral Health 30-day Hospital readmission rate
Small AIM
Reduce no-shows for post-hospital appointments to Outpatient Services
(Psychiatry Services, AODA Day Treatment, and Mental Health/AODA Therapy)
Project Aims

## Slide 3
Changes (Do)
Identified one element of the “Warm Hand-off”– familiarity of location for post-hospital services
Determine location of focus (Wausau, Merrill/Tomahawk, or Antigo)
Educate Inpatient staff on the “Warm Hand-off” process
Track number of post-hospital appointments to Outpatient Services
Track the no-show rate of post-hospital appointments to Outpatient Services
North Central Health Care | NIATx Project 2013

## Slide 4
Results (Study)
North Central Health Care | NIATx Project 2013
BIG AIM: Re-admissions (30-day re-admission rate) have increased.
Benchmark = 4.8%
Warm Hand-off = 9.1%
SMALL AIM: No show rate for post-hospital outpatient appointments.
Benchmark = 57%
Warm Hand-off = 36%
Ongoing tracking of number of post-hospital appointments scheduled at Outpatient Services
Ongoing tracking of no-show rate of post-hospital appointments

## Slide 5
Next Steps (Act)
North Central Health Care | NIATx Project 2013
ADAPT
Schedule hospital discharge appointments with client’s consent
Provide options to clients who decline scheduling of a post-hospital appointment with Outpatient Services
Consider barriers
Identify reasons for client no-shows

## Slide 6
Impact (Lessons Learned)
Implementing a significant change project is accomplished most successfully by starting with a very thorough evaluation process (Plan) utilizing process improvement tools such as the Cause & Effect Fishbone Diagram
Decisions based on data are easily supported by leadership and employees
Team-based decision making and employee engagement is critical to the success of a change project
Process-Improvement initiatives require the involvement of high-performing employees
North Central Health Care | NIATx Project 2013