## Slide 1: Outagamie County Department of Health and Human Services
Mental Health Division

## Slide 2: Project AIMS
Big Aim
Decrease our inpatient hospital readmission rate
Small Aim
Increase access to outpatient mental health services through the implementation of a walk-in clinic by reducing the waiting time for services from five weeks to one business day

## Slide 3: Changes
Conducted a complete Walk-Through.
Currently analyzing data to determine hospital readmission rates.
Procedure and Structure of the Walk-In Clinic went through four rounds of critical review until a “Final Draft” was agreed upon.

## Slide 4: Results
The Walk-In Clinic has been approved by the Manager/Clinical Director of the Mental Health Division.
The Walk-In Clinic has not been reviewed or approved by the Director of the Department of Health and Human Services.

## Slide 5: Next Steps
We are optimistic that the Walk-In Clinic will be operational in 2014.
Several steps will need to occur in order for this to occur: cooperation amongst several units and divisions including: Fiscal, Support Staff, Crisis Unit, Administration, and Outpatient Clinicians.

## Slide 6: Impact
Change is a Process.
The Mental Health Division will continue to push for the implementation of a Walk-In Clinic. This, along with appropriate Hospital Diversion, will decrease out County readmission rate and increase access to outpatient services in Outagamie County.