## Slide 1
NIATx/State of WI
Mental Health Collaborative
Reduce Waiting & No-Shows  Increase Admissions & Continuation

## Slide 2: Background
Big Aim…
Reduce hospital readmissions

## Slide 3: Areas to Improve:
Front-door
Treatment
Back-door (& beyond)

## Slide 4: Next Steps:
Continue what you have started
Sustain
New aim?

## Slide 5: Let The Presentations Begin!

## Slide 6: Rock Stars
Improving service to
clients by decreasing
length of time from
intake to connection
with a provider

## Slide 7: Project Aim
Decrease length of time between request for services and entry into treatment to no greater than 2 weeks.
Specific Population: Clients admitted to Residential Crisis Stabilization following a hospitalization or other mental health crisis

## Slide 8: Changes
1. Added 4 hours/week of additional time for intake/assessments
2. Changed protocol to perform assessments on site at Stabilization facility prior to discharge vs. after discharge at the outpatient clinic.

## Slide 9: Results
Chart: Days between Harper's Place Admission and Assessment Completion
| Before Change | After Change
 | 24 | 5

## Slide 10: Results
Chart: Average Days between Harper's Place Admission and Client Entering Outpatient care
| Before Change | After Change
 | 38 | 20
Chart: Harper's Place Admission/Assessment/Therapy
| Before Change | After Change
Days to Assessment Completion | 24 | 5
Days to Entering Therapy | 14 | 15

## Slide 11: Adopt Adapt Abandon
Adopt increased staff time dedicated to Assessments
Adopt on site assessments at Stabilization Facility
NEXT: improve scheduling processes to decrease length of time to enter outpatient schedules
NEXT: expand mobile assessments to include sites other than crisis stabilization facility

## Slide 12: Impact
37% decrease in length of time between assessment and entry into care
Earlier and improved engagement and customer service by providing on site assessments
Improved satisfaction of Crisis Stabilization staff with more solid discharge plan in place