## Slide 1: Sauk County Department of Human Services
NiaTx Project 2013

## Slide 2: Niatx 2012 Goals
Big Aim:
  Reduce (re-) hospitalizations due to gaps in service delivery when consumers’ needs are immediate, multiple, and/or exceed existing plan of care
Small Aim:
  Create a plan to evaluate and assist consumers within 48 hrs to reduce duplication of services, staff time, and that is person centered
Changes:
Defined Intervention Therapist position
Trained all SCDHS staff in team process and collaboration
Implemented monthly work group meetings for administration and staff to enhance intra-agency communication

## Slide 3: Niatx 2013 Goals
Big Aim:
  Reduce (re-) hospitalizations/out of home placements for children and youth due to gaps in services delivery when consumers’ needs are immediate, multiple, and/or exceed existing plan of care
Small Aim:
  Initial contact with family will be made within 48 hours of referral
  Intervention Recovery Plan and Crisis Plan (if needed) will be completed within 30 days of initial contact
  Facilitate family/consumer engagement in needed and appropriate services within 6 months
Changes:
Hired/implemented Intervention Therapist position within the Mental Health and Recovery Services Unit
Introduced position to each unit
Developed a referral process and billing sequence
Continued monthly collaborative work group

## Slide 4: Results
March-September 2013
Scope of services divided in 2 tracks to respond to needs of Sauk County
  Complex crisis cases involving families are routed for interventionist assignment via MHRS manager
  OR internal staff can make referrals by first discussing with unit supervisors, then by referring to MHRS manager
100% of families assigned contacted within 48 hours
Intervention plans created within 30 days (if needed)
  Crisis Plans 100%
  Recovery Plans 66%
Within 6 months families have been transitioned to services as needed, both within county programs and to outside community providers

## Slide 5: Next Steps
Formalize a family assessment tool and the process for disseminating this information to stakeholders
Collect and analyze data compared to prior years once sample size is larger or a full year of implementation has passed
Better define appropriate referrals to the Intervention Therapist
Develop alternative resources to address gaps, ie. child psychiatry, respite, parent coaching
Further consider SCDHS response to consumers who don’t share the goal of reducing hospitalizations/out of home placements
Consider expanding services to adult consumers within a family unit

## Slide 6: Success Story * 8 year old boY and mom in crisis arrive at scdhs with local law enforcement requesting hospitalization. Family has limited knowledge of services and lacks social support.
$4,800.00
$1,000.00
On-call response
  On-call crisis worker assesses for hospitalization with a “snap shot” of the family needs.
  If unable to divert, minimum costs incurred include 3 days of hospitalization under an emergency detention.
  If hospitalization is diverted, limited follow-up is provided, leading to higher likelihood for future crisis.
Early Intervention Response
  Case is routed for Intervention to stabilize the child in a least restrictive setting and evaluate underlying familial needs.
  A Children’s Services Crisis Network home is used for 5 days while assessment and services are arranged.
  Follow-up crisis intervention is provided for 2 months until family is stable.