## Slide 1: NIATx Change Project 2014
Community Recovery Works
Jefferson County Human Services
Community Support Program

## Slide 2: THE AIMS
Reduce the time from referral to admission in CSP by 50%
Reduce hospital admissions by providing more intensive CSP services more quickly to consumers who have acute mental health needs

## Slide 3: The Change
1. Review all consumers in CSP for the ability to graduate to less intensive services which will still meet their current mental health needs.
2. Formally review consumer’s progress prior to each treatment plan to evaluate options for less intensive services while providing for mental health needs.

## Slide 4: The Results
Chart: Days from Referral to Admission in CSP
| Days to Admission | .
Pre Change | 75 | 0
Post Change | 13 | 0
Column1

## Slide 5: Action
Adopted both changes
Implemented an ongoing process to identify consumers interested in receiving less intensive supports
Incorporated in several treatment plans a step down of services to prepare for outpatient clinic or CCS services in the future

## Slide 6: The Impact
Cleared the CSP waiting list
Allowed quicker admission for the consumers experiencing the most acute mental health needs in the county
Allowed several consumers to be admitted to CSP at discharge from their hospitalizations
Provided tangible evidence to consumers who were discharged of their own progress in their recovery and achievement of their goals