## Slide 1: Increasing Communication and it’s Positive Impact Juneau County Department of Human Services and Juneau County Law Enforcement Agencies
Scott Ethun director—executive sponsor
JoAnn Geiger, LPC Behavioral health and clinic manager—change leader
Mariah Soderling daytime crisis worker
Mary Jo Onsager, LCSW Community Support Manager
Colleen James, LCSW Afterhours crisis
Mauston Police Department
Juneau county sheriff’s office
Elroy police department
Wonewoc-center police department
New lisbon police department

## Slide 2: Project Aim
Big Aim
  Decrease the number of emergency detentions by doing better assessments, utilizing least restrictive means and collaborating/communicating with Law Enforcement/DHS/CRISIS
Small Aim
  Reduce the number of emergency detentions during daytime crisis hours by 50% from (baseline) 2 per month to (goal) an average of 1 per month by October 1, 2016.

## Slide 3: Rapid Cycles
RATIONALE:
Original process:
  Law Enforcement would call our general number and be triaged through our phone tree and get to our intake workers who would take a message and get it to the daytime crisis worker.
Hypothesis developed by Change Team:
  More direct access to Crisis worker will provide for better communication.
Walk Through
  Phone tree issues discovered
  Repetition of relaying of information
ACTIONS:
LAW ENFORCEMENT DIRECT LINE TO CRISIS WORKER
From May 9 through May 20 we had Mauston PD call directly to daytime crisis worker.
  ADAPTED as we struggled to get the direct phone number to all officers
    Some forgot to put number in their phones
    Directed LE who called JoAnn to correct individual
From June 6 to June 30 we added Elroy PD, Wonewoc-Center PD and New Lisbon PD call directly to daytime crisis worker.
  ADAPTED
    Same issues as above
From July 18 to August 5 all Law Enforcement, including now Juneau County Sheriff’s Office were to call directly to daytime crisis worker.
  ADOPTED

## Slide 4: Results
Chart: 
| May | June | July | August | Sept
Daytime Chapters 2015 | 1 | 1 | 2 | 4 | 3
Chart: 
| May | June | July | August | Sept
Daytime Diversions 2015 | 5 | 1 | 0 | 2 | 1
Chart: 
| May | June | July | August | Sept
Daytime Chapters 2016 | 0 | 0 | 1 | 0 | 0
Chart: 
| May | June | July | August | Sept
Daytime Diversions 2016 | 6 | 7 | 10 | 10 | 5

## Slide 5: Impacts
Shared interest in utilizing least restrictive means for individuals in crisis
Increased communication on all levels with all jurisdictions and crisis
Improved relationships between JCDHS and LE
If LE and Crisis are on the same page it is easier to work with the other systems (e.g. Physicians)
Better collaboration between Crisis and LE
Positive financial impact for all partners
Positive consumer impact

## Slide 6: Next Steps
CELEBRATE successful project!
Look at Afterhours and how we can change that process for LE contact.
SUSTAINABILITY PLAN:
Policy and procedure of the process
Future thinking—new hires for all systems involved
  How do we communicate to new hires in all departments/contracts
  Identification of a sustain leader