## Slide 1: Behavioral Health Services of Racine County
Improving Follow-Up Response Time
Executive Sponsor : Michelle Goggins
Division Manager
Change Leader : Mary Jane Whitmore, LCSW, CSAC
Clinical Director
Natalie Meinert, LCSW – Crisis/APS Supervisor
Nicole Cremona – Mobile Response Worker
Javier Luna – Mobile Response Worker
Boyd Schwartz and Christina Dudzinski, LPC left during the project.

## Slide 2: Aim
Big Aim: Decrease Racine County’s readmission rate.
Small Aim:
  +/- 90% for contacts within 24 – 48 hrs
  Focused on 2nd contacts during 48 hrs – 30 day window.
  Improve the timeliness and quality of follow up contact by the Mobile Response Unit. Will improve contact with consumers after the initial 24-48 hour window by 10%.
Base Line – average 75%
Goal – 85%

## Slide 3: Change
Define what constitutes a meaningful contact.
  Meaningful Contact – actual phone conversation, completed home visit or meeting with the consumer, or admission into the SAIL program.
  Some overlap between cycle 1 and 2 because “meaningful contact” needed further explanation. Confusing for some workers.
Add additional white board for Mobile Responders to clearly identify consumers in need of 2nd contact and date of last contact.
  Adaption - Have the board closer to the Mobile Response work area so that it remains in their line of sight and more difficult to overlook.

## Slide 4: Results
Improved 2nd contacts to 82.5%
Unable to determine September results due to a change in our reporting system.
Chart: 
| May | June | July | Aug (after 1st change)
Baseline Ave | 75 | 75 | 75
% of successful 2nd contacts | 82.5

## Slide 5: Next Steps
Sustaining the first cycle.
  The adopted definition was told to staff; working on formalizing.
  Incorporating the standard while training new staff.
Adapting the white board from the 2nd cycle.
Future cycles being considered:
  Improved communication with shareholders.
  Assigning consumers to each worker to follow up with.
  Re-organizing staffing patterns.

## Slide 6: IMPACT
With cost savings due to hospitalizations, it will ensure that Racine County’s limited resources are effectively utilized which could mean hiring additional workers or upgrading technology/facilities.
It will also has a trickle down effect with other units and with consumers.
  Case load size in Ongoing Crisis, CCS, and CSP are manageable and effective.
  SAIL consumers will be appropriate for that level of care.
Lessons Learned
  Be sure that changes are well communicated to all staff and shareholders.
  Keep ideas for change concise. Don’t over think the change project or rapid cycles.
  Some community influences are out of your control, i.e. change in admission policies at local hospitals, floods, etc.