## Slide 1: Streamline CSP Comprehensive Assessment Process
Rock County CSP Change Team
Heidi Lammon, Shawna Mills, Karol Rosman, Nancy Story, Lindsey Scianna, Amy Gustafson, Patrick Bailey
Nadine Westby-Risley, Change Leader
Kate Luster, Executive Sponsor

## Slide 2: AIM
Big Aim
Decrease Rock County hospital readmission rates
Small Aim
Streamline and create a more relevant assessment process for new CSP clients. To accomplish this, we will reduce the time between admission to CSP and the time it takes to complete the assessment and enter it in to Avatar’s Comprehensive Assessment form.
Baseline: Start of project on average 90 days to complete. Our goal is to reduce this to 30 days.

## Slide 3: Change
Redesigned forms and changed the procedure for completing the assessment.
1.) March 1, case managers start putting assessment narrative directly into Avatar.
  -Narrative assessment is typed into Avatar, directly tied to billing, successfully reduces the number of days to complete each section
2.) May1, present information about the new client as we get it, not waiting 30 days for the case review.
-presenting known information about the client prior to starting the assessments
-present information gained after each assessment area is complete at next morning meeting
3.) September 1, began using new assessment forms in different stages of revision.
4.) October 1, put all changes into a formalized procedure.

## Slide 4: Results
Chart: 
| 42323 | 42374 | 42377 | 42384 | 42416 | 42629 | 42659
Days to Complete | 99 | 85 | 81 | 94 | 91 | 6 | 25

## Slide 5: Next Steps-Sustain Plan
Each CSP team’s supervisor will continue to monitor average days to complete the assessment. If exceeding 30 days, staff will review and analyze the procedure, defining potential changes to return to, and sustain, the 30 day baseline.
Continue to obtain feedback from staff and clients regarding the relevance and user friendliness of the forms, and continue to change them as appropriate.

## Slide 6: Impact
Impact to clients
Less intrusive and intimidating to new clients
Decrease repetition of questions, one less section of the assessment
Culturally relevant and trauma informed questions
Better initial 6 month Person Centered Plan
Since January, no re-hospitalizations for new clients at JSCP
Impact to Treatment Team/Rock County
Decrease in repetitive documentation
Aids to identify clients stage of change for treatment planning/interventions
Easier for engagement of new clients, which can prevent early hospitalizations.
Gives the psychiatrist a better 30 day case review
Decreases hospitalizations reduces financial burden to the county