## Slide 1: AODA Follow-Up within 7 Days
Wood County Human Services Department
Outpatient Behavioral Health Clinic and Norwood Health Center
Wisconsin Rapids and Marshfield, WI
Karen Brewer, Tina Garnick, Heather Grys-Luecht, Stephanie Gudmunsen,
Susan Schuler-Sheveland, Kristi Smith, Bev Spencer

## Slide 2: AIM: What are we trying to accomplish?
Reduce wait time to outpatient AODA follow-up appointment from 5 weeks (estimated) to 1 week post-discharge.
Target Population: All Wood County residents hospitalized on the Admissions Unit at Norwood Health Center (Wood County inpatient behavioral health unit) that require follow-up primary AODA treatment and who will be receiving follow-up care through outpatient services at Wood County Human Services Outpatient Clinic.
Notes: Why the team chose to focus on the population – point in time, data context, a few problematic cases

## Slide 3: Changes made Steps taken…
Brainstorming and nominal group technique applied to generate change ideas and prioritize ideas to test
Rapid Cycle 1 (8/1/16-9/30/16): Assign a “point person” to manage appointments for the target population
  Negotiate with front desk, billing, counselors to “find” an appointment and schedule within 7 days post-discharge
  Talk to discharge planners/social workers to ensure transportation or learn of any other barriers
  Follow-up with reminder call and encouragement to patient prior to appointment

## Slide 4: How does your project grow?
Results:
Cycle was planned to last from 2 to 4 weeks
Cycle lasted 8 weeks due to limited data being captured
From the four data points gathered, it was determined that 75% of target population was scheduled for first follow-up appointment within 7 days
Far too small a sample to understand if this change was really effective

## Slide 5: Discoveries
1) There aren’t really that many primary AODA diagnosed patients in the target population
2) May not really have a problem in the target population. The baseline of 5 weeks was an estimate and are only now really seeking a true baseline of the broader population, which will include the target as a subset
3) May have a customer service process problem because we don’t know how or if possible to bill for concurrent dual intake. Haven’t had many dual certified therapists so clients needed to see two clinicians; most clients are coming in with dual dx, but process requires a choice of one over the other…hence the discovery of the limited primary AODA population
4) The bigger problem is getting people to come to their appointments rather than scheduling the first f/u within 7 days
Just like non-farm kids digging potatoes for the first time…we discovered many hidden nuggets of wonder and learning

## Slide 6: What’s next?
Evaluate process of follow-up outpatient appointments for customer service focus and possibility of offering both MH/AODA intake in one appointment
Redefine target population – team is refocusing with better data
With four dual certified clinicians, attempt to utilize dual certified clinicians for dually diagnosed clients as much as possible
Clarify billing processes for dual diagnosis and treatment
Put processes in writing to ensure agreement and consistency
Continue to evaluate processes to identify gaps and opportunities for improvement