## Slide 1: Readmission Reduction Project – Dodge County
Team: Kim Kunz, Sara Gaska, Emily Jorgenson, Melissa Abel

## Slide 2: AIM
Dodge County will reduce readmissions from our baseline of 8.9% to a goal of 5% by October 15, 2017.

## Slide 3: CHANGE
First Cycle: Consistent follow-up phone calls to consumer released from hospital within 72 hours of discharge. (3.13.17-5.12.17)
Second Cycle: Ensure the consumer is connected with the appropriate level of care upon discharge from hospital; continuing with follow-up phone calls/in-person office visit. (7.3.17-8.4.17)
Third Cycle: Complete a warm handoff prior to discharge from hospital (crisis staff or community programs staff). (8.15.17-9.15.17)

## Slide 4: RESULTS
Cycle 1: 25 admissions; one re-admitted within 30 days; 4 re-admitted within 90 days.
  Success! Our readmission rate was 4%, which was an overall decrease.
Cycle 2: 12 admissions; 1 re-admitted within 30 days
  Success! We did find that most individuals were within the appropriate level of care, but a few that were not were able to be connected with appropriate services.
Cycle 3: 14 admissions; no individuals were re-admitted within 30 days.
  Success! Crisis or Community program staff attempting to see prior to discharge.
Overall: 51 admissions during this project with only 2 re-admissions within 30 days.
Final Achievement: Our goal was a 30 day re-admission rate of 5% and we ended with a re-admission rate of 3.9%!

## Slide 5: Next steps
ADOPT CHANGES!
Continue with warm hand off (if possible) prior to discharge
Continue with follow up phone call with in 24-48 hours of discharge
Continue to ensure consumer is involved in the appropriate level of care

## Slide 6: Impact
Initial re-admission rate for Dodge County was 8.9% with a goal of 5%
Final Achievement: 30 day re-admission rate was 3.9%
Allowed us to better service consumers
Able to be creative and utilize community program staff in warm hand off
Ensure consumers are receiving appropriate level of care
Ensure a discharge plan is set in place with appointments already set
Fiscal impact – decrease in dollars going to WMHI or other locations.